# Project SUMMARY

| Project/ Name | RIF 1 project CONAS 012 Utilization of the Potential of ornamental fish species for training and business development in Uganda. |
| --- | --- |
| Project Sponsor | Government of the Republic of Uganda to Makerere University |
| Project PI | Dr. Juliet Kigongo Nattabi |
| Start Date | Dec 2019 | Completion Date | June 2021 |

# Project Closure SUMMARY

## Purpose of the project

Production of animals for the aquarium hobbyist trade is a rapidly growing sector of the aquacultural industry, and it will continue to become more important as restrictions are placed on collecting animals from the wild. Currently, approximately 90% of freshwater fish traded in the hobbyist industry are captively cultured. Given the future importance of aquaculture production of ornamental species, it is important to elucidate the benefits and risks for this sector. There are over 300 species of Haplochromine widely distributed in Ugandan lakes with a huge potential for ornamental trade but not exploited. Moreover, most ornamental fish fetch much higher economic value than food fish, they may provide a good alternative livelihood option for fishers and the lakeside dependent communities (Kannan, 2014, Namulawa, et al. 2014). In 2015, Uganda ranked 129 in export of ornamental live fish (Factfish, 2018), however, the ornamental fish industry is still under-developed and limited in knowledge of available ornamental fish species. One of the sustainable ways of resource utilization is through artificial culture; our project therefore intended to undertake a robust collection, identification and breeding potential ornamental species, starting with the haplochromine cichlids fish species from the Lake Victoria basin

The Department of Zoology, Entomology and Fisheries Science located at the College of Natural Sciences, Makerere University has had a moderate outdoor aquarium facility since its inception in the 1940s which is of aesthetic value and an indoor aquarium facility with 17 tanks which were not fully functional due to limited funding towards development of teaching aid infrastructure. With Support from the government of Uganda to Makerere University RIF one. The indoor aquarium facility has been fully refurbished and   currently stocked with  upto 13 fish species unique and some on the verge of extinction majorly collected from the Lake Nabugabo ecosystem during samplings. If fully expanded in the training-business perspectives and diverse collections undertaken, the available facilities and ornamental fish collections provide huge potential for training and income generation.

## Objectives achieved/not achieved

1.	To revamp the Aquarium facility at ZEFS for educational training and create awareness on ornamental fishes through training.

2.	To collect diverse specimens of haplochromine fish species and other ornamental fish species from the Lake Victoria and its satellite lakes.

3.	To identify and document the occurrence and distribution of ornamental fish species in the study lakes

4.	To conduct selective breeding of wild haplochromine species for ex-situ conservation and aquarium business promotion through tourism and aesthetic value addition

5.	Develop guidelines for ornamental aquaculture and trade in Uganda.

NB Objectives 1-3 were achieved while objective 4and 5 are/were not and we will be seeking for funding both internal and external later on to accomplish them.

## Outputs

- A fully equipped and refurbished training and research aquarium facility available for students of Fisheries and Aquaculture and other allied courses within the vicinity of University premises.

- Innovation of a Solar powered fish transport tank that uses conversion  DC to AC   for aeration during transit of live fish from field to aquarium resulting in the removal of using oxygen cylinders to transport fish over long distances

- 17 fish species have been collected

- Identification of the species documented and distribution pending input int GIS of points sampled

## engangement pictures

## media mentions

## Lessons Learned

12 species were identified from the sampling and stocked in the aquarium and their morphological characteristics described

Four of the above species have been identified as potential aquarium species as they are hardy pending breeding except one is being prepared for breeding.